## Sheet1
	task	team	start	end	completion_frac	dependencies
0	Write Specification	R&D	01/06/24	30/06/24	1
1	Collect User Profiles	Warehouse	02/06/24	15/06/24	1
2	Review Specification	Sales	03/06/24	25/06/24	1
3	Design	R&D	01/07/24	15/07/24	1	Write Specification,Review Specification
4	Electronic Requirements	Dr Plum	15/07/24	28/07/24	1
5	Mechanical Requirements	Ms Smith	16/07/24	01/08/24	0.95
6	Software Architecture	IT	17/07/24	02/09/24	0.7
7	PCB Build	Sales	01/08/24	15/08/24	0.35	Electronic Requirements
8	PCB Debug	Dr Plum	15/08/24	30/08/24	0.1
9	Mechanical Build	Robotic Armz	03/08/24	20/08/24	0	Mechanical Requirements
10	Integration	Ms Smith	01/09/24	09/09/24	0	PCB Debug,Mechanical Build
11	Software Development	IT	10/09/24	10/10/24	0